## Sheet1
System Name | Stay Easy | Host and Booking Management System
Members: | Pajares, Josemar
Te, Jushua Peter
Medallo, Christian Jay
Statuses |  | Todo
In-Progress
Done
On-hold
[5 empty] | August |  |  |  | September
Tasks | Assignee | Date Started | Date Finished | Status | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
1. LOGIN
1.1. Creating UI | Medallo, Christian Jay | 2024-09-02 |  | In-Progress | bar: August 3
1.2. Integrate with DB | B | 2024-08-22 | 2024-08-30 | bar: August 3 to August 4
2. LOGOUT | C | 2024-08-20 | 2024-08-23 | In-Progress | bar: August 3
1 System ERD | Pajares | 2024-08-31 | 2024-09-01 | Done | bar: September 1
1 Creating User & Transaction Database Layout | Te, Jushua Peter | 30/8/2024 | 2024-09-01 | Done

## Sample Dire
System Name | Stay Easy
Members: | Pajares, Josemar
Te, Jushua Peter
Medallo, Christian Jay
Statuses |  | Todo
In-Progress
Done
On-hold
[5 empty] | August |  |  |  | September
Tasks | Assignee | Date Started | Date Finished | Status | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
1. LOGIN
1.1. Creating UI | B | 2024-08-21 | 2024-08-21 | Todo | bar: August 3
1.2. Integrate with DB | B | 2024-08-22 | 2024-08-30 | bar: August 3 to August 4
2. LOGOUT | C | 2024-08-20 | 2024-08-23 | In-Progress | bar: August 3